## README
AGENCY — CAPACITY VS DEMAND PLANNER
RangeLead.com ¦ Auto-Calculated Spreadsheet
PURPOSE
Compare team capacity against project demand to identify gaps, hiring triggers, overtime risk, and optimal team sizing. Plan resource allocation across upcoming projects.
REQUIRED INPUTS (INPUT sheet)
• Team members with role, available hours per month
• Project pipeline: name, hours needed, deadline month
• Maximum overtime hours per person (CONFIG)
OUTPUTS (OUTPUT sheet)
• Monthly capacity vs demand comparison
• Gap/surplus per month
• Hiring trigger alerts
• Overtime risk assessment
• Optimal team size recommendation
DO NOT EDIT
• LOGIC sheet — contains all calculations
• OUTPUT sheet — displays results from LOGIC
• CONFIG sheet — contains constants and rates
HOW TO USE
• Go to the INPUT sheet and fill in the yellow-highlighted cells
• Results auto-calculate instantly on the OUTPUT sheet
• Adjust CONFIG values only if you understand the assumptions

## CONFIG
CONFIGURATION — Capacity Assumptions
Working Days Per Month | 22 | Standard business days
Hours Per Day | 8 | Standard work day
Max Overtime Hours/Person/Month | 20 | Before burnout risk
Target Capacity Utilization | 85% | Leave buffer for admin/meetings
Hiring Lead Time (months) | 2 | Time to onboard new hire
Overtime Cost Premium | 1.5 | Overtime hourly rate multiplier
Avg Hourly Cost Per Person | 65 | Blended labor rate
Capacity Danger Threshold | 95% | Above this = overloaded
Capacity Warning Threshold | 80% | Above this = getting tight

## INPUT
TEAM ROSTER — Enter your data in yellow cells
Team Member | Role | Available Hrs/Mo | Hourly Cost ($)
Sarah J. | Senior Designer | 176 | 85
Mike C. | Developer | 176 | 95
Lisa P. | Developer | 176 | 90
James W. | Junior Designer | 176 | 55
Anna S. | Content Writer | 176 | 60
Tom B. | PM | 176 | 75
PROJECT PIPELINE — Upcoming demand
Project Name | Priority | Month 1 Hrs | Month 2 Hrs | Month 3 Hrs | Month 4 Hrs | Month 5 Hrs | Month 6 Hrs
Website Redesign | High | 200 | 300 | 250 | 100 | 0 | 0
Mobile App | High | 0 | 150 | 350 | 400 | 300 | 200
Brand Campaign | Medium | 120 | 80 | 60 | 0 | 0 | 0
SEO Overhaul | Medium | 60 | 60 | 60 | 60 | 60 | 60
Content Series | Low | 40 | 40 | 40 | 40 | 40 | 40
Analytics Setup | High | 80 | 40 | 20 | 0 | 0 | 0

## LOGIC
CALCULATIONS — All formulas, do NOT edit
TEAM CAPACITY
Active Team Members
Total Available Hours/Month
Effective Capacity (with buffer)
Max Capacity (with overtime)
Avg Cost/Hour (blended)
6-MONTH CAPACITY VS DEMAND
Metric | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6
Total Demand (hrs)
Available Capacity
Max Capacity (with OT)
Gap / Surplus (hrs)
Capacity Utilization %
Status
Overtime Hours Needed
Overtime Cost
Hiring Trigger?
OPTIMAL TEAM SIZING
Peak Demand (hrs)
Avg Demand (hrs)
Hours Per Person (effective)
Optimal Size (for peak)
Optimal Size (for average)
Current Team Size
Headcount Gap (vs peak)
Headcount Gap (vs average)
Total 6-Month Overtime Cost
Months Requiring Overtime

## OUTPUT
CAPACITY VS DEMAND — RESULTS
Auto-calculated from your inputs
TEAM CAPACITY
Team Size
Total Available Hours/Month
Effective Capacity (with buffer)
Max Capacity (with overtime)
OPTIMAL TEAM SIZE
Optimal Size (for peak)
Optimal Size (for average)
Headcount Gap (vs peak)
Sizing Verdict
OVERTIME & COST RISK
Total 6-Mo Overtime Cost
Months Requiring Overtime
6-MONTH FORECAST
Metric | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6
Total Demand
Capacity
Gap / Surplus
Utilization %
Status
Overtime Hours
Overtime Cost
Hiring Trigger
RangeLead.com ¦ Premium B2B Lead Data ¦ Free Download — rangelead.com/free-tools