## README
HR - WORKFORCE CAPACITY PLANNER
RangeLead.com ¦ Auto-Calculated Spreadsheet
PURPOSE
Match team capacity against project demand. Identify which teams are over/under-utilized, quantify skill gaps, and determine hiring urgency to meet upcoming project needs.
REQUIRED INPUTS (INPUT sheet)
• Teams with FTE counts and available hours/FTE/month
• Primary skill for each team
• Projects with required hours per month
• Skills required per project
• Project priority (High/Medium/Low)
OUTPUTS (OUTPUT sheet)
• Capacity vs demand per team
• Utilization rate by team
• Skill gap analysis
• Hiring urgency (how many FTEs needed)
• Overall organization utilization
• Project coverage status
DO NOT EDIT
• LOGIC sheet — contains all calculations
• OUTPUT sheet — displays results from LOGIC
• CONFIG sheet — contains constants and rates
HOW TO USE
• Go to the INPUT sheet and fill in the yellow-highlighted cells
• Results auto-calculate instantly on the OUTPUT sheet
• Adjust CONFIG values only if you understand the assumptions

## CONFIG
CONFIGURATION — Constants & Assumptions
Working Hours Per Month | 160 | Standard monthly hours per FTE
Productive Utilization Target | 80% | Target % of available hours on projects
Max Sustainable Utilization | 95% | Above this = burnout risk
Overhead/Admin Allocation (%) | 15% | Non-project time (meetings, admin, etc.)
Hiring Lead Time (months) | 3 | Time from req to productive new hire
Cost Per FTE Per Month ($) | 8500 | Fully loaded cost per employee per month
Contractor Premium (%) | 50% | Premium for contractors vs FTE cost

## INPUT
WORKFORCE INPUTS — Enter your data in yellow cells
TEAM CAPACITY
Team Name | FTEs | Hours/FTE/Month | Primary Skill | Planned Leave Hours | Open Positions
Frontend Dev | 8 | 160 | JavaScript | 80 | 1
Backend Dev | 10 | 160 | Python | 120 | 2
DevOps | 4 | 160 | Infrastructure | 40 | 0
Design | 5 | 160 | UI/UX | 60 | 1
QA | 6 | 160 | Testing | 48 | 0
Data Science | 3 | 160 | Analytics | 24 | 1
Mobile Dev | 4 | 160 | Mobile | 32 | 1
PROJECT DEMAND
Project Name | Hours/Month | Skill Required | Duration (months) | Priority | Status
Website Redesign | 320 | JavaScript | 4 | High | Active
API Platform v2 | 480 | Python | 6 | High | Active
Mobile App Launch | 400 | Mobile | 5 | High | Active
CI/CD Pipeline | 160 | Infrastructure | 3 | Medium | Active
Dashboard Analytics | 240 | Analytics | 4 | Medium | Active
Design System | 200 | UI/UX | 3 | Medium | Active
Performance Testing | 160 | Testing | 2 | Low | Planned
Data Migration | 120 | Python | 2 | Low | Planned

## LOGIC
CALCULATIONS — All formulas, do NOT edit
TEAM CAPACITY ANALYSIS
Team | Gross Capacity (hrs) | Net Capacity (hrs) | Demand (hrs) | Surplus/Deficit | Utilization % | FTEs Needed | Hiring Urgency | Status
ORGANIZATION SUMMARY
Total Teams
Total FTEs
Total Gross Capacity
Total Net Capacity
Total Demand
Overall Utilization
Total FTEs to Hire
Open Positions Already
Additional Hires Needed
Monthly Hiring Cost
Contractor Cost (if used)
Active Projects
Planned Projects
Overloaded Teams
Capacity Health

## OUTPUT
WORKFORCE CAPACITY — RESULTS
Auto-calculated from your inputs
ORGANIZATION OVERVIEW
Total FTEs
Total Net Capacity
Total Demand
Overall Utilization
Capacity Health
HIRING REQUIREMENTS
FTEs to Hire
Open Positions Already
Additional Hires Needed
Monthly Hiring Cost
Contractor Alternative Cost
Overloaded Teams
PROJECT STATUS
Active Projects
Planned Projects
TEAM BREAKDOWN
Team | Utilization | Surplus/Deficit | Hires Needed | Status
RangeLead.com ¦ Premium B2B Lead Data ¦ Free Download — rangelead.com/free-tools