## README
PROJECT COST ESTIMATOR
RangeLead.com ¦ Auto-Calculated Spreadsheet
PURPOSE
Estimate total project cost by phase, including labor, materials, and contingency. Track burn rate and per-deliverable costs.
REQUIRED INPUTS (INPUT sheet)
• Project phases with description
• Resources per phase (roles, hours, hourly rates)
• Material costs per phase
• Contingency percentage
• Number of deliverables per phase
OUTPUTS (OUTPUT sheet)
• Cost per phase (labor + materials)
• Total project cost with contingency
• Cost per deliverable
• Monthly burn rate estimate
• Phase cost breakdown percentages
• Budget status indicators
DO NOT EDIT
• LOGIC sheet — contains all calculations
• OUTPUT sheet — displays results from LOGIC
• CONFIG sheet — contains constants and rates
HOW TO USE
• Go to the INPUT sheet and fill in the yellow-highlighted cells
• Results auto-calculate instantly on the OUTPUT sheet
• Adjust CONFIG values only if you understand the assumptions

## CONFIG
CONFIGURATION — Constants & Assumptions
Default Contingency % | 10% | Applied to total estimated cost
Overhead Multiplier | 1.15 | Indirect costs (facilities, admin)
Project Duration (months) | 6 | Estimated project timeline
Budget Limit | 500000 | Maximum approved budget
Working Hours / Day | 8 | Standard working hours per day
Working Days / Month | 22 | Average working days per month

## INPUT
PROJECT COST INPUTS — Enter your data in yellow cells
Phase | Role / Resource | Hours | Hourly Rate | Material Cost | Deliverables | Phase Budget | Priority | Notes
Discovery | Project Manager | 80 | 125 | 2000 | 3 | 50000 | High
Discovery | Business Analyst | 120 | 95 | 500 | 3 | 50000 | High
Design | UX Designer | 160 | 110 | 3000 | 5 | 80000 | High
Design | UI Designer | 120 | 105 | 1000 | 5 | 80000 | Medium
Development | Senior Developer | 320 | 150 | 5000 | 8 | 200000 | High
Development | Junior Developer | 400 | 85 | 0 | 8 | 200000 | Medium
Development | DevOps Engineer | 80 | 130 | 8000 | 2 | 200000 | Medium
Testing | QA Lead | 120 | 100 | 2000 | 4 | 60000 | High
Testing | QA Tester | 200 | 70 | 500 | 4 | 60000 | Medium
Deployment | DevOps Engineer | 60 | 130 | 10000 | 2 | 40000 | High
Deployment | Project Manager | 40 | 125 | 1000 | 2 | 40000 | Low

## LOGIC
CALCULATIONS — All formulas, do NOT edit
PER-LINE LABOR & COST CALCULATIONS
Phase | Role | Labor Cost | Material Cost | Line Total | With Overhead | % of Total
TOTALS
SUMMARY METRICS
Total Labor Cost
Total Material Cost
Subtotal (Before Overhead)
Total With Overhead
Contingency Amount
Grand Total (With Contingency)
Monthly Burn Rate
Daily Burn Rate
Budget Remaining
Budget Utilization %
Budget Status
Total Hours
Avg Cost Per Hour
Total Deliverables
Avg Cost Per Deliverable

## OUTPUT
PROJECT COST ESTIMATOR — RESULTS
Auto-calculated from your inputs
COST SUMMARY
Total Labor Cost
Total Material Cost
Subtotal
Overhead Applied
Contingency
GRAND TOTAL
BURN RATE & BUDGET
Monthly Burn Rate
Daily Burn Rate
Budget Remaining
Budget Utilization
Budget Status
EFFICIENCY METRICS
Total Hours
Avg Cost Per Hour
Total Deliverables
Avg Cost Per Deliverable
RangeLead.com ¦ Premium B2B Lead Data ¦ Free Download — rangelead.com/free-tools