## README
RESOURCE ALLOCATION PLANNER
RangeLead.com ¦ Auto-Calculated Spreadsheet
PURPOSE
Plan and optimize resource allocation across multiple projects. Detect over-allocation conflicts and track utilization rates.
REQUIRED INPUTS (INPUT sheet)
• Resource names and available hours per week
• Project names and required hours per resource
• Allocation matrix (hours assigned per resource per project)
OUTPUTS (OUTPUT sheet)
• Resource utilization percentage per person
• Project staffing completeness
• Over-allocation conflict detection
• Optimal allocation suggestions
• Team-wide utilization summary
DO NOT EDIT
• LOGIC sheet — contains all calculations
• OUTPUT sheet — displays results from LOGIC
• CONFIG sheet — contains constants and rates
HOW TO USE
• Go to the INPUT sheet and fill in the yellow-highlighted cells
• Results auto-calculate instantly on the OUTPUT sheet
• Adjust CONFIG values only if you understand the assumptions

## CONFIG
CONFIGURATION — Constants & Assumptions
Standard Hours / Week | 40 | Normal work week hours
Max Utilization Target | 85% | Healthy max utilization %
Over-Allocation Threshold | 100% | Flag if utilization exceeds this
Weeks in Period | 4 | Planning period in weeks
Overhead Hours / Week | 5 | Meetings, admin, etc.

## INPUT
RESOURCE ALLOCATION — Enter your data in yellow cells
RESOURCES & AVAILABILITY
Resource Name | Avail Hrs/Wk | Rate ($/hr) | Website Redesign | Mobile App | CRM Upgrade | Data Migration | API Gateway | Security Audit | Cloud Setup | Analytics
Alice Johnson | 40 | 125 | 10 | 15 | 5 | 0 | 0 | 0 | 0 | 0
Bob Smith | 40 | 95 | 0 | 20 | 10 | 8 | 0 | 0 | 0 | 0
Carol Davis | 40 | 110 | 15 | 0 | 0 | 0 | 10 | 10 | 0 | 0
Dan Wilson | 40 | 130 | 0 | 0 | 0 | 20 | 0 | 0 | 15 | 0
Eve Martinez | 40 | 85 | 0 | 0 | 5 | 0 | 15 | 0 | 0 | 20
Frank Lee | 32 | 150 | 8 | 0 | 0 | 0 | 0 | 16 | 8 | 0
Grace Kim | 40 | 100 | 0 | 10 | 20 | 0 | 0 | 0 | 0 | 10
PROJECT REQUIRED HOURS / WEEK
Required Hrs/Wk |  |  | 25 | 40 | 30 | 28 | 25 | 26 | 23 | 30

## LOGIC
CALCULATIONS — All formulas, do NOT edit
RESOURCE UTILIZATION
Resource | Total Allocated | Available | Net Available | Utilization % | Website Redesign | Mobile App | CRM Upgrade | Data Migration | API Gateway | Security Audit | Cloud Setup | Analytics
PROJECT STAFFING SUMMARY
Metric | Website Redesign | Mobile App | CRM Upgrade | Data Migration | API Gateway | Security Audit | Cloud Setup | Analytics
Total Allocated Hrs
Required Hrs
Hours Gap
Staffing %
Status
TEAM SUMMARY METRICS
Total Team Available Hrs/Wk
Total Team Allocated Hrs/Wk
Team Net Available Hrs/Wk
Avg Team Utilization
Over-Allocated Resources
Under-Utilized Resources
Total Resources
Active Projects
Period Cost (Allocated Hrs)
Conflict Score
Health Status

## OUTPUT
RESOURCE ALLOCATION — RESULTS
Auto-calculated from your inputs
TEAM OVERVIEW
Total Resources
Active Projects
Total Avail Hrs/Wk
Total Allocated Hrs/Wk
Net Available Hrs/Wk
UTILIZATION & CONFLICTS
Avg Team Utilization
Over-Allocated Resources
Under-Utilized Resources
Period Labor Cost
Allocation Health
RESOURCE DETAIL
Resource | Allocated | Available | Net | Utilization
RangeLead.com ¦ Premium B2B Lead Data ¦ Free Download — rangelead.com/free-tools